Comprehensive Field Engineering Monograph

Volume 3: UST Construction Standards, Engineering Procedures, and Site Commissioning Protocols

Prepared by: GPT-4o Expert Research Division
Industry Scope: UST Installation Engineering, Petroleum Infrastructure Construction, and Code Compliance

### 1. Site Evaluation and Civil Planning Requirements

#### 1.1 Geotechnical Assessment

- Perform ASTM D2487 soil classification to assess soil bearing capacity (target >2000 psf for UST pad)

- Conduct GPR and magnetometer scans for subsurface obstructions

- Survey elevation contours and model fuel flow path using hydrodynamic terrain modeling (e.g., HEC-RAS integration)

#### 1.2 Permitting and Compliance Package

- Submit scaled drawings (1:20 or 1:40) to AHJ

- Incorporate setback requirements per NFPA 30A: 10 ft from property line, 25 ft from public right-of-way

- Ensure NEPA clearance for environmentally sensitive zones; include SPCC plan

#### 1.3 Site Staging and Material Laydown

- Designate Class II laydown zone for fiberglass tank staging (non-reactive bedding)

- Include RFI (Request for Information) queue and BIM coordination with electrical and mechanical trades

### 2. Tank Bedding, Placement, and Anchoring

#### 2.1 Excavation and Bedding

- Excavate to minimum 18–24” beyond tank diameter; verify with laser level to ±0.25”

- Use pea gravel or crushed stone (ASTM D448 #8) with compaction to 95% Standard Proctor

- Install geotextile barrier to separate bedding from native soil

#### 2.2 Tank Lowering Procedure

- Utilize rated nylon or Kevlar straps; rated minimum 3x tank weight

- Avoid steel cables to prevent shell abrasion or dielectric compromise

- Monitor strain on straps using load cell or digital dynamometer

- Confirm tank pitch (slope) of 1/8” per foot for product drainage toward suction tube

#### 2.3 Anchoring Methodologies

- For high water table sites (>3 ft from base):

  - Use concrete deadmen anchors with stainless steel turnbuckles and tensioning rods

  - Confirm anchor load to exceed buoyant uplift force: V = (Vwt - Wt) x safety factor (≥1.5)

- Torque straps to manufacturer specification (typically 150–250 ft-lbs) and verify with torque wrench

### 3. Piping Systems Installation – Pressure and Vent

#### 3.1 Primary and Secondary Containment

- All piping must be double-walled (UL 971 listed), with interstitial space integrity tested per PEI RP100

- Secondary piping must maintain slope of 1/8” per foot toward containment sump

- Install entry boots with compression or mechanical seal; torque to 35–50 in-lbs

#### 3.2 Vent Line Configuration

- Use Schedule 40 galvanized steel or flexible composite UL-listed material

- Vent must terminate minimum 12’ above grade, 10’ from openings or intakes

- Add P/V vent cap to maintain atmospheric pressure and mitigate vapor escape (2.5” WC pressure, 6.0” WC vacuum)

#### 3.3 Pressure Piping Standards

- Pressurized piping must be tested to 150% of operating pressure for minimum 1 hour

- Install shear valves in accordance with NFPA 30A, 514.11(B)(1): must trip within 125 lbs of lateral force

### 4. Electrical Infrastructure and Control Integration

#### 4.1 Conduit and Seal-offs

- All conduits entering classified zones must have explosion-proof seal-offs within 18”

- Use epoxy resin sealing compound with appropriate damming fiber to prevent migration

- Bond conduit to grounding electrode system with resistance <1 ohm

#### 4.2 Wiring and Isolation

- Use THHN/THWN-2 conductors in wet locations

- Maintain minimum separation of 12” between AC and low-voltage signal cables

- Install isolation barriers on POS to STP controller paths using opto-isolators or relays

#### 4.3 Control Systems Commissioning

- Install Veeder-Root, Incon, or OPW tank monitor console in climate-controlled building

- Validate probe readings using certified meter stick and water-finding paste

- Program tank chart and perform span calibration of sensors

### 5. Backfill, Surface Restoration, and Site Commissioning

#### 5.1 Layered Backfill Protocol

- Place backfill in 12” lifts, compacted to 95% Proctor Density

- Use clean pea gravel or sand (<5% fines) in direct contact with tank surface

- Document compaction results and submit density logs per lift for inspector signoff

#### 5.2 Concrete Pad and Island Construction

- Minimum 6” thick pad with 4000 psi concrete; 12” for high-traffic areas

- Include vapor barrier and rebar mat tied per ASTM A615 Grade 60

- Install expansion joints every 10’ and control joints every 5’ in slab

#### 5.3 System Commissioning and Certification

- Hydrostatic test spill buckets and sumps (1 hr no-drop test)

- Conduct precision tank test using ATG (0.1 GPH)

- Perform line tightness test (0.1 GPH @ 150% pressure for 1 hr)

- Submit as-built drawings, equipment serial logs, pressure test certificates, and inspection checklists

Conclusion: Volume 3 presents a construction-phase protocol with engineering-level precision and regulatory compliance embedded at each critical point. From subgrade preparation to final system commissioning, this document equips construction managers and field engineers with a blueprint for durable, compliant, and verifiable UST installations in high-demand commercial fuel environments.